## Action Tracker
Post-Incident Action and Lessons Tracker
Use alongside the SIRV Post-Incident Review Template. Keep completion evidence separate from effectiveness evidence where an effectiveness check is required.
Total actions | 0 | Open | 0 | Overdue | 0 | Effectiveness check due | 0 | Closed | 0
Action ID | Incident / review ref | Finding / lesson | Agreed action | Owner | Date agreed | Due date | Completion evidence required | Status | Completion evidence checked | Completion date | Effectiveness check required? | Effectiveness review date | Outcome / effectiveness evidence | Further action required | Retained learning | Applies elsewhere? | Closed by | Closed date | Overdue?

## Worked Example
Worked example: fictional contractor tailgating incident
This example is illustrative. It shows how actions can be tracked through completion, effectiveness checking and retained learning without treating 'complete' as the final step.
Action ID | Incident / review ref | Finding / lesson | Agreed action | Owner | Date agreed | Due date | Completion evidence required | Status | Completion evidence checked | Completion date | Effectiveness check required? | Effectiveness review date | Outcome / effectiveness evidence | Further action required | Retained learning | Applies elsewhere? | Closed by | Closed date | Overdue?
A-01 | PIR-2026-014 | Contractor arrival instruction did not clearly require reception sign-in before controlled access. | Amend contractor joining instructions to state that all contractors must report to reception before entering controlled areas. | Facilities Manager | 2026-09-03 | 2026-09-12 | Approved revised instruction and evidence it has entered use. | Effectiveness checked | Revised instruction approved and issued to contractor coordinators. | 2026-09-11 | Yes | 2026-10-15 | Revised instruction used during the next contractor mobilisation and reception process followed. |  | Where contractor access depends on reception sign-in, arrival instructions should state the required entry route explicitly. | Yes | Security Manager | 2026-10-16
A-02 | PIR-2026-014 | Staff guidance included anti-tailgating expectations but the point had not featured in recent briefings. | Include tailgating and challenge expectations in the next staff security briefing. | Security Manager | 2026-09-03 | 2026-09-18 | Briefing material and attendance record. | Effectiveness checked | Briefing delivered and attendance recorded. | 2026-09-17 | Yes | 2026-12-18 | A later reported event showed an employee challenging a person before allowing entry. Unreported tailgating cannot be ruled out. |  | Access technology should be considered alongside user behaviour and challenge arrangements where tailgating remains possible. | Yes | Head of Security | 2026-12-19
A-03 | PIR-2026-014 | It was not known whether similar reliance on staff behaviour existed at other controlled entrances. | Review other controlled staff entrances for the same exposure and record any further findings. | Security & Facilities | 2026-09-03 | 2026-09-25 | Recorded site review covering all controlled staff entrances. | Complete | Site review completed; no additional material weakness recorded. | 2026-09-24 | No |  |  |  |  | Yes | Security Manager | 2026-09-25

## Guidance
How to use this tracker
Purpose | Use the tracker for actions accepted through a post-incident review. Keep the action, completion evidence and effectiveness evidence distinct.
Minimum fields | For every accepted action, record the action, owner, due date and completion evidence required.
Effectiveness | Use an effectiveness check where the consequence, uncertainty or importance of the change warrants it. 'Complete' does not by itself prove that a control works in practice.
Closure | Use 'Closed' only when required completion evidence has been checked and any required effectiveness check has been completed or consciously resolved by the accountable person.
Retained learning | Record a lesson only when it is specific enough to inform a later related decision. Avoid vague statements such as 'staff should remain vigilant'.
Boundary | This is a SIRV practical working resource, not a prescribed standard. Keep accountable judgement with the appropriate person and follow any formal investigation, legal or regulatory process that applies.
Status | Use when
Agreed | Action accepted but not yet started.
In progress | Work has started.
Completion evidence submitted | Owner says the action is complete and evidence is awaiting review.
Complete | Completion evidence has been checked. No effectiveness check is required, or the action now moves to 'Effectiveness check due'.
Effectiveness check due | The action is complete but the planned effectiveness review has not yet been performed.
Effectiveness checked | The planned effectiveness review has been carried out.
Further action required | The outcome or effectiveness review shows that more work is needed.
Closed | The action can be closed after required evidence and effectiveness checks have been resolved.