## Start Here
Contractor RAMS Review and Pre-start Verification
Editable checklist, action record and decision trail ¦ Version 1.0 ¦ September 2026
Completing this record does not approve RAMS, prove that controls exist in practice, establish that the work is safe or authorise work to begin. Document review, checks at the work location and any permit or authorisation process remain distinct. Accountable decisions stay with the people who hold the appropriate competence and authority.
This is a practical framework, not a legal procedure prescribed for every organisation or task. Adapt it to the work, contractual arrangements, relevant dutyholder roles and your organisation's controls. The legal references concern Great Britain; Northern Ireland has separate legislation and regulatory guidance.
How to use this workbook
1. Enter the job and document details below, then complete each question on the Document Review sheet using the available response list.
2. Record the document reference or evidence supporting each response. Move material gaps, questions and dependencies into Actions & Revisions.
3. Select one document-review outcome on this sheet. The workbook does not calculate or recommend an outcome.
4. Complete Pre-start Check at the work location and record the separate permit or authorisation reference where your local process requires one.
Job and review details
Contractor |  | Project or contract
Task |  | Exact work location
Planned date and time |  | Site or client
RAMS title |  | RAMS version and issue date
Review owner |  | Review started
Live summary indicators
Review responses (of 34) | Responses needing attention | Open actions | Pre-start items outstanding
0 | 0 | 0 | 0
Document-review outcome - record one human decision
Selected outcome
Reviewed version |  | Review date
Reviewer |  | Specialist referral or record
Reasoning and conditions
Use 'Ready to progress to pre-start checks and authorisation' only to record completion of the document review. It does not confirm site conditions, issue a permit or authorise the work. Material unresolved matters should remain visible and be managed through the applicable process.
Detailed guidance: https://getsirv.com/2026/07/contractor-rams-review-checklist/
Note on A28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Counts recorded responses only. A numerical completion count is not a safety score and does not determine the document-review outcome.
Note on E28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Counts populated action rows unless their status is Closed or Withdrawn.

## Document Review
Stage 1 - Contractor RAMS document review
Record what the submitted documents actually say. A 'Yes' should be supported by evidence; 'Not applicable' should include a reason. Move material gaps and dependencies into the action log.
Ref | Review area | Review question | Response | Evidence or document reference | Reviewer comment or finding | Action ID
1.1 | Submission and scope | Does the submission identify the contractor, project, exact work location, task and planned timing?
1.2 | Submission and scope | Are the document version, issue date and responsible author or reviewer clear?
1.3 | Submission and scope | Are the scope, exclusions and limits of the work defined?
1.4 | Submission and scope | Does the submission reflect the site, client and pre-construction information supplied?
1.5 | Submission and scope | Are interfaces with occupants, members of the public, other contractors and nearby activities addressed?
2.1 | Risk assessment | Are the hazards specific to the task, location, equipment and expected conditions?
2.2 | Risk assessment | Does the assessment identify who may be harmed and how?
2.3 | Risk assessment | Are the existing and proposed controls clear enough to be understood and acted upon?
2.4 | Risk assessment | Are relevant specialist or task-specific assessments identified?
2.5 | Risk assessment | Are assumptions, dependencies and unresolved actions visible?
2.6 | Risk assessment | Where further controls are required, are the action owner and completion point recorded?
2.7 | Risk assessment | Is the reasoning clear, rather than relying only on a completed risk matrix or residual-risk score?
3.1 | Method statement | Does the method describe a logical sequence from arrival and set-up through completion and handback?
3.2 | Method statement | Are the proposed access arrangements, equipment, plant, materials and working methods clear?
3.3 | Method statement | Are controls described at the stage of work where they will be needed?
3.4 | Method statement | Is the method consistent with the hazards and controls in the risk assessment?
3.5 | Method statement | Are emergency, rescue or stop-work arrangements included where relevant?
3.6 | Method statement | Does the method explain how the area will be left secure and handed back?
3.7 | Method statement | Is any generic or copied wording contradicted by the actual job details?
4.1 | People, competence and coordination | Are supervision and other important responsibilities clear?
4.2 | People, competence and coordination | Are the necessary skills, knowledge, training, experience or authorisations identified?
4.3 | People, competence and coordination | Are induction, briefing and communication arrangements addressed?
4.4 | People, competence and coordination | Is coordination with other contractors, site teams and affected operations explained?
4.5 | People, competence and coordination | Do the proposed people, time and resources appear consistent with the described method?
5.1 | Supporting controls and dependencies | Are required permits, isolations, access controls or other authorisations identified?
5.2 | Supporting controls and dependencies | Are relevant supporting documents, certificates, inspection records or specialist assessments included or referenced?
5.3 | Supporting controls and dependencies | Are responsibilities belonging to the contractor, client, site team or another party distinguished?
5.4 | Supporting controls and dependencies | For construction work, is the submission consistent with relevant pre-construction information, the construction phase plan and CDM arrangements?
5.5 | Supporting controls and dependencies | Are dependencies that must be completed before work starts clearly recorded?
6.1 | Review record and consistency | Do names, dates, locations, equipment and work details agree across the submission?
6.2 | Review record and consistency | Have all missing, unclear or conflicting points been recorded?
6.3 | Review record and consistency | Has each required action been given an owner and completion point?
6.4 | Review record and consistency | Are the reviewed version, reviewer, date, outcome and reasoning recorded?
6.5 | Review record and consistency | Can the selected outcome be supported by the evidence contained in the submission?

## Actions & Revisions
Actions, questions and revision history
Use one row for each material gap, clarification, dependency or specialist referral. Close an item only when the required evidence has been reviewed and the closure decision is recorded.
Action ID | Related review item | Gap, question or decision | Required action or response | Owner | Completion point | Status | Revised document or version | Response received | Closure evidence | Closed by | Closed date
A-001
A-002
A-003
A-004
A-005
A-006
A-007
A-008
A-009
A-010
A-011
A-012
A-013
A-014
A-015
A-016
A-017
A-018
A-019
A-020
A-021
A-022
A-023
A-024
A-025
A-026
A-027
A-028
A-029
A-030
A-031
A-032
A-033
A-034
A-035
A-036
A-037
A-038
A-039
A-040

## Pre-start Check
Stage 2 - Pre-start verification at the work location
Complete these checks at the work location. Do not complete this stage solely by rereading the documents. A permit, isolation or other authorisation remains a separate process where required.
Ref | Verification area | Check | Status | Evidence or local record | Responsible person | Date and time verified | Notes or action
P1 | Task and conditions | Do the actual task, location, timing and site conditions still match the reviewed submission?
P2 | People | Are the expected workers and supervisor present?
P3 | Competence and authority | Have any required competence or authorisation checks been completed?
P4 | Communication | Have the current RAMS and any revisions been communicated and understood?
P5 | Communication | Have the required inductions and briefings been completed?
P6 | Equipment and controls | Are the specified equipment, plant and physical control measures present and suitable for use?
P7 | Site arrangements | Are access, exclusion, emergency and welfare arrangements in place where applicable?
P8 | Permits and isolations | Have required permits been issued and necessary isolations confirmed through the authorised process?
P9 | Coordination | Has coordination with other work, occupants and affected people been confirmed?
P10 | Outstanding actions | Have all outstanding document-review actions been closed?
P11 | Change control | Have any changes to the conditions, people, equipment or proposed method been identified?
P12 | Change control | If a material change has been identified, has it been assessed through the applicable process before work begins?
P13 | Accountable decision | Has the appropriate accountable person made the separate decision that work may start?
Record of the separate local decision or authorisation
This block records a decision made under the organisation's own process. It does not create authority, issue a permit or replace an isolation or permit-to-work record.
Local decision status |  |  |  | Decision or authorisation reference
Accountable person |  |  |  | Role or authority
Decision date and time |  |  |  | Permit or isolation references
Conditions or notes
If the task, conditions, people, equipment or proposed method have changed materially, stop and use the applicable change and assessment process before work begins.

## Sources & Notes
Sources, scope and use notes
This is a practical framework, not a legal procedure prescribed for every organisation or task. Adapt it to the work, contractual arrangements, relevant dutyholder roles and your organisation's controls. The legal references concern Great Britain; Northern Ireland has separate legislation and regulatory guidance. Completing this record does not approve RAMS, prove that controls exist in practice, establish that the work is safe or authorise work to begin. Document review, checks at the work location and any permit or authorisation process remain distinct. Accountable decisions stay with the people who hold the appropriate competence and authority.
Source | What it supports | URL
SIRV contractor RAMS review checklist | Detailed explanation of the two-stage framework and its boundaries | https://getsirv.com/2026/07/contractor-rams-review-checklist/
HSE - Managing risks and risk assessment at work | Hazards, affected people, controls, action ownership and review | https://www.hse.gov.uk/simple-health-safety/risk/steps-needed-to-manage-risk.htm
Management of Health and Safety at Work Regulations 1999, regulation 3 | General risk-assessment duty in Great Britain | https://www.legislation.gov.uk/uksi/1999/3242/regulation/3
HSE - Construction administration and method statements | Method-statement purpose and construction examples | https://www.hse.gov.uk/construction/safetytopics/admin.htm
HSE - Using contractors | Defining work, exchanging information, coordination and supervision | https://www.hse.gov.uk/pubns/indg368.htm
HSE - Contractors: roles and responsibilities | CDM contractor duties, competence, supervision and coordination | https://www.hse.gov.uk/construction/cdm/2015/contractors.htm
Construction (Design and Management) Regulations 2015 | Current CDM legislation | https://www.legislation.gov.uk/uksi/2015/51/contents
HSE - Appoint a competent person | General description of competence in health and safety assistance | https://www.hse.gov.uk/simple-health-safety/gettinghelp/index.htm
HSE - Permit to work systems | Permit distinction and relationship with risk assessment | https://www.hse.gov.uk/humanfactors/topics/ptw.htm
Review and handling notes
Check current legislation, official guidance, contractual arrangements and local controls before adopting this workbook.
The appropriate reviewer depends on the work, organisation, contract and relevant dutyholder arrangements. Refer specialist or technically complex matters to someone with suitable expertise.
Store and share completed records according to their sensitivity, retention requirements and your organisation's information controls.
Workbook version 1.0, September 2026. Source article: https://getsirv.com/2026/07/contractor-rams-review-checklist/